## schedule
Activity ID | Activity Name | Predecessors | Optimistic Time | Most Likely Time | Pessimistic Time
A | Site Clearance |  | 2 | 4 | 6
B | Foundation Excavation | A | 3 | 5 | 9
C | Concrete Pouring | B | 2 | 3 | 4
D | Framing | B | 4 | 6 | 8
E | Roofing | D | 3 | 5 | 6
F | Plumbing | C,D | 2 | 4 | 6
G | Finishing | E,F | 1 | 2 | 3